Rotary Club Yearbook Project Charter

Table of Contents
## Section 1. Charter Introduction

Revision Number	Date of Issue	Author(s)	Brief Description of Change
1.0	2017-01-11	Chris Hein	Created Document
1.1	2017-01-15	Andrew Rehberg	Updated to include Dependencies information
1.2	2017-01-15	Chris Hein	Updated to finalize deliverables information

### 1.1 Authorization
This Project Charter, for the redevelopment of the Rotary Club Yearbook website has been reviewed in full and approved by the following:
Signature_______________________________________________

## Section 2. Project Overview
### 2.1 Project summary
- In broad terms the project is straight forward in concept: the updating of the existing yearbook website for the Rotary Club. This includes the existing login system, the sponsor page, the photographer page and the solicitor page. This will also include smaller scale improvements such as a consistent design across the entire site and an easier to use, more intuitive and less complicated interface for pages that currently require them. The purpose is to improve the usability of the site from the admin, photographer and user end, as well as to include requested enhancements, as outlined below
- The client has requested the following specific additions be made to the site:
- A system wherein when a client submits a picture/ad for approval to the Rotary Club, it is approved (or rejected) prior to an invoice being generated for payment
- An automated invoice system. Invoices that are automatically generated, stating what was ordered by the client, and sent to the clients contact email address, after an ad has been ordered and approved
- A system that allows for emails to be checked/verified as an actual valid and current email address by the Rotary Club. This is to ensure they can send invoices and contact the client if necessary
- A system that allows for a client to view their chosen ad details and comments they have included (and change if necessary) before submitting their request for an ad
- (added by the developers) A system to allow the user to reset/retrieve their password when needed
- A more user friendly, use and manage version of the reports page
- The ability to easily select the size of ad the client wishes to purchase
- A system that allows for the photographer(s) involved with an ad to view the client assigned to them as well as related important details (contact info, when and where the shoot will be, etc.)
- A simple search system added to the report page that allows the Rotary Club to search through data by key information such as business, client name, contact information, etc... and return data related to the search

### 2.2 Project scope

#### 2.2.1 Scope definition
In Scope:
- High level bullet list of things that will be implemented by the team in terms of the project
- Implementation of consistent design theme for all the pages
- Rewrite of login system to be easier to deal with on the back end and to support password recovery
- Redesign and rewrite of sponsor page
- Redesign and rewrite of photographer page
- Redesign and rewrite of solicitor page
- Redesign and rewrite of the ad creation and approval system
- Creation of the automated invoice system
- Creation of the email verification system
- Simplified redesign and rewrite of the reports page
- Implementation of a system wherein the photographer assigned to a client has access to important information regarding that client
- Restructuring of the existing database to support the changes made to the existing site
- Implementation of a basic search system for the reports page

Out of Scope:
- Website hosting
- Long term support
- Implementation or support for the sites chosen billing system (we just ensure invoices are generated when necessary based on info obtained via the website)
### 2.3 Deliverables

Project Deliverable 1:	Confirmation Email
Description:	A generated email that will be sent to the client with their information and photograph that is approved by an administrator.
Acceptance criteria:	Client and project manager
Due date:	March 20th 2017
Dependencies:	Master Page, Database Redesign
Project Deliverable 2:	Administrator Front End
Description:	Redesign the front end of the administrator site for usability
Acceptance criteria:	Client
Due date:	April 1st 2017
Dependencies:	Master Page
Project Deliverable 3:	Administrator Ownership Data Display
Description:	Administrator can assign solicitors specific lists of businesses
Acceptance criteria:	Client
Due date:	March 1st 2017
Dependencies:	Database Redesign
Project Deliverable 4:	User Confirmation
Description:	Once info is saved, user needs to be able to see image and text info they entered so they can approve it prior to info being sent to rotary club
Acceptance criteria:	Client
Due date:	March 20th 2017
Dependencies:	Front End Design
Project Deliverable 5:	Automated Invoice
Description:	Generated invoice that the Solicitor or Administrator approves then sends to the business.
Acceptance criteria:	Client
Due date:	March 20th 2017
Dependencies:	Front End and Back End development
Project Deliverable 6:	Password Reset on Login page
Description:	User can reset a login password if they have forgotten, sending it to the appropriate email account
Acceptance criteria:	Client
Due date:	January 31st 2017
Dependencies:	Master Page, Back End Development, Database redesign

Project Deliverable 7:	Front End Master Page
Description:	A master page to create a consistent layout across all pages
Acceptance criteria:	Client
Due date:	January 31st 2017
Dependencies:	None
Project Deliverable 8:	Redesign Database
Description:	Redesign the database to reflect the changes required
Acceptance criteria:	Project Lead
Due date:	January 31st 2017
Dependencies:	None
Project Deliverable 9:	Photographers Front End
Description:	Design photographers page to include efficient layout and functionality, including approval of photographs, and a response section to the business photos.
Acceptance criteria:	Client
Due date:	March 15th 2017
Dependencies:	Master Page
Project Deliverable 10:	Solicitor Front End
Description:	Develop Front End to include specific business checklist dependant on the login criteria. Contact information of the assigned businesses as well as pending requests from the businesses
Acceptance criteria:	Client
Due date:	March 15th 2017
Dependencies:	Master Page, Database Redesign

Project Deliverable 11:	Redesign Login System
Description:	Rewrite the login system to eliminate pointless and over complicated usage of ajax/json
Acceptance criteria:	Project Lead
Due date:	January 31st 2017
Dependencies:	None

Project Deliverable 11:	Sponsor Front End
Description:	Rewrite of the sponsor front end to fit with the rest of the new site design and operation
Acceptance criteria:	Project Lead
Due date:	March 15th 2017
Dependencies:	Master Page, Database Redesign

### 2.4 Project cost estimate and sources of funding
 As the existing site is already hosted by the nscc, no additional hosting requirements should be needed, at least in the scope of our project. There are no funding requirements.

	Hours	Wage	Total Cost

Totals			$0.00

## Section 3. Project Organization
### 3.1 Roles and responsibilities

Role	Description	Name/Title
Developer	Front End Development	Matt Hutchinson
Developer	Database and back end development	Chris Hein
Developer	User interface design and back end development	Andrew Rehberg
Testing	Contribute opinion, testing, knowledge and other personal resources	Entire team
Project Lead	Upkeep direction, documentation, and organization	Chris Hein
Subject Matter Expert	Broad knowledge of implementation and development	Entire team
Senior Project Manager	Approval for budget, and oversee deliverables are met.	Sean Morrow

### 3.2 Project facilities and resources

- Access to labs 308 and 312 as needed
- Access to meeting room 215 as needed for client meetings
- Access to student web space for live server testing
- Access to existing site files and database

## Section 4. Glossary and Acronyms
Define all terms and acronyms required to interpret the project charter properly.
Term or Acronym	Definition
Solicitor Page	Page that clients use to select an ad to purchase and provide related data
Sponsor Page	Page that Rotary Club admin uses to view and approve ad applications from clients
Photographer Page	Page that handles image and ad management, as well as admin access